## Slide 1
CORE COMPONENT
Project Management and Risk Assessment
Core Paper 1
Specification reference: 2.8, 2.9
Digital Support and Security T Level · Lesson slides
Unofficial teaching resource. Check the official Pearson specification for assessment detail.

## Slide 2
CORE COMPONENT · Core Paper 1
Learning objectives
Digital Support and Security T Level · Project Management and Risk Assessment
2
By the end of this lesson you should be able to:
1
Build and interpret a 5 by 5 risk matrix.
2
Describe what risk assessment documentation should record.
3
Compare Waterfall and Agile project methodologies.
4
Interpret and draw Gantt, PERT, Kanban, precedence and critical path diagrams.
STARTER
You are installing 30 new PCs in a school over half term. What could go wrong? Which of those risks worries you most?

## Slide 3
CORE COMPONENT · Core Paper 1
The 5 by 5 risk matrix
Digital Support and Security T Level · Project Management and Risk Assessment
3
Likelihood \ Severity | Negligible | Marginal | Moderate | Critical | Catastrophic
Frequent (5) | 5 | 10 | 15 | 20 | 25
Probable (4) | 4 | 8 | 12 | 16 | 20
Occasional (3) | 3 | 6 | 9 | 12 | 15
Remote (2) | 2 | 4 | 6 | 8 | 10
Improbable (1) | 1 | 2 | 3 | 4 | 5
Risk score = likelihood x severity. Higher scores need action first.
Notes: Severity runs 1 (negligible) to 5 (catastrophic). Ask students to place three risks from the starter on the grid.

## Slide 4
CORE COMPONENT · Core Paper 1
Risk assessment documentation
Digital Support and Security T Level · Project Management and Risk Assessment
4
A description of the risk
Who or what could be harmed, and how
Mitigations already in place
Further mitigation needed
Who is responsible, and the due date
!
KEY IDEA
Risk assessments exist to ensure continuity of service, health and safety, and regulatory compliance.

## Slide 5
CORE COMPONENT · Core Paper 1
Waterfall and Agile
Digital Support and Security T Level · Project Management and Risk Assessment
5
Waterfall
Linear stages completed in order
Requirements fixed at the start
Easy to plan, budget and document
Hard to change once a stage is finished
Suits projects with clear, stable requirements
Agile
Short iterations delivering working pieces
Requirements evolve with feedback
Frequent contact with the customer
Harder to predict final cost and date
Suits projects where needs will change

## Slide 6
CORE COMPONENT · Core Paper 1
Project management techniques
Digital Support and Security T Level · Project Management and Risk Assessment
6
1
Gantt chart
Bars on a timeline showing when each task starts and ends.
2
PERT chart
Network of tasks with optimistic, likely and pessimistic time estimates.
3
Precedence table
Lists each task and the tasks that must finish before it.
4
Kanban
Board of cards moving through columns such as To do, Doing, Done.
5
Critical Path Analysis
Finds the longest chain of dependent tasks: the shortest possible project length.
Notes: Task 1 of the Employer Set Project asks students to produce a Gantt chart, so give this plenty of practice.

## Slide 7
CORE COMPONENT · Core Paper 1
Finding the critical path
Digital Support and Security T Level · Project Management and Risk Assessment
7
List every task with its duration and dependencies (a precedence table).
Draw the tasks as a network in dependency order.
Add up the duration along every route from start to finish.
The longest route is the critical path.
A delay to any task on it delays the whole project.
!
KEY IDEA
Tasks not on the critical path have float: spare time they can slip without delaying the finish.

## Slide 8
CORE COMPONENT · Core Paper 1
Check your understanding
Digital Support and Security T Level · Project Management and Risk Assessment
8
1
A risk is 'probable' and 'critical'. What is its score?
2
Name three things a risk assessment should record.
3
Which methodology suits a project whose requirements will change?
4
What does a Gantt chart show?
5
What happens if a task on the critical path is delayed?
Notes: Give students a few minutes to answer on mini whiteboards or paper, then reveal the answers on the next slide.

## Slide 9
CORE COMPONENT · Core Paper 1
Answers
Digital Support and Security T Level · Project Management and Risk Assessment
9
1
A risk is 'probable' and 'critical'. What is its score?
4 x 4 = 16.
2
Name three things a risk assessment should record.
Any three of: description, who/what could be harmed, how, existing mitigations, further mitigation, owner, due date.
3
Which methodology suits a project whose requirements will change?
Agile.
4
What does a Gantt chart show?
When each task starts and finishes on a timeline.
5
What happens if a task on the critical path is delayed?
The whole project is delayed.
Notes: Talk through any answers the class found difficult.

## Slide 10
CORE COMPONENT · Core Paper 1
Activity: Plan the PC rollout
Digital Support and Security T Level · Project Management and Risk Assessment
10
30 minutes
Small groups
1
Tasks: order kit (5 days), image PCs (3), remove old PCs (1), install desks and cabling (2), install new PCs (2), test (1).
2
Build a precedence table for the tasks.
3
Draw a Gantt chart and find the critical path.
4
Score the three biggest risks on the 5 by 5 matrix.
SUCCESS CRITERIA
Dependencies are realistic
Gantt chart is to scale
Critical path identified with its total length
Each risk has a mitigation and an owner

## Slide 11
CORE COMPONENT · Core Paper 1
Exit ticket
1
What is the highest possible score on a 5 by 5 matrix?
2
Give one drawback of Waterfall.
3
What does float mean in critical path analysis?
REVISE THIS TOPIC
Revision notes for this lesson are on the study wiki:
Core Paper 1: Problem Solving, Digital Support and Data
https://lana6478.github.io/Digital-Suport-and-security-T-levle/#/01-core-component/01-core-paper-1.md
Notes: Students answer on a sticky note or in the chat before leaving.